|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | **OpCon 5**  | **OpCon 4** | **OpCon 3** | **OpCon 2** | **OpCon 1** |
| **Forecast Event**  | **Normal Operations and Atlantic Basin Monitoring** | **Potential impacts Within 120 hours** | **Potential impacts within 72 hours** | **Potential impacts within 48 hours** | **Potential impacts within 24 hours** |
| **Major Weather Events:** |  |  |  |  |  |
| **Decision Points** |  Continue day-to-day activities.  | * Decision to convene an internal GEMA Conference Call?
* Decision to convene County Coordination Call?
* Decision to convene ESF Conference Call?
 | * Decision to convene an internal GEMA Conference Call?
* Decision to convene County Coordination Call?
* Decision to convene ESF Conference Call?
 | * Decision to Activate Emergency Ops Command and SOC?
* Decision to establish a Joint Information Center?
* Decision to request a Governor's State of Emergency Declaration?
* Decision to initiate Wireless Emergency Alerts?
 | * Decision to convene Conference Call(s)?
* Decision to request a Presidential Disaster Declaration?
* Decision to request direct federal assistance?
* Decision to initiate Wireless Emergency Alerts?
 |
| **GEMA Meteorologist** | * Continue day-today activities: monitor weather models, NOAA products, local broadcast meteorologist’ forecast, radar trends, etc.

 * Monitor the Atlantic Basin (Atlantic Ocean, Gulf of Mexico, and Caribbean Sea) and disseminate information on any existing / threatening storms.
 | * Continue day-to-day activities.
* Monitor the Atlantic Basin (Atlantic Ocean, Gulf of Mexico, and Caribbean Sea) and disseminate information on any existing / threatening storms.
* Consult the Director of Operations on whether any course of action needs to be taken.
 | * Continue day-to-day activities.
* Consult with the Director of Operations on what course of action should be taken.
 | * Continue day-to-day activities.
* Consult with the Director of Operations on what course of action should be taken, including:
	+ Meet with the GEMA Director and Deputy Directors;
	+ Consult the Weather Advisory Group (WAG);
	+ Notify local EMA Directors, area field coordinators, area school safety coordinators, and GEMA Weather Distribution List;
	+ Meet with Public Affairs Officer (PAO) to construct proper messaging.
 | * Continue day-to-day activities.
* Consutl with the Director of Operations on what courses of action should be taken, including:
	+ Communicate with GEMA Director, Deputy Directors, Division Directors, and certain ESF partners;
	+ Consult the Weather Advisory Group;
	+ Notify local EMA Directors, area field coordinators, area school safety coordinators, and GEMA Weather Distribution list;
	+ Meet with GEMA Public Affairs Officer (PAO) to construct proper messaging.
 |
| **GEMA State Warning Point** | * Day-to-Day Activities.
* Maintain Situational Awareness of Weather in Georgia.
* Monitor Weather Bug Website.
* Monitor NWS Chat.
* Monitor Open Source Media.
* Disseminate Incident and Damage Reports resulting from Weather Events.
 | * Day-to-Day Activities.
* Maintain Situational Awareness of Weather in Georgia.
* Monitor Weather Bug Website.
* Monitor NWS Chat.
* Monitor Open Source Media.

Disseminate Incident and Damage Reports resulting from Weather Events.  | * Day-to-Day Activities.
* Maintain Situational Awareness of Weather in Georgia.
* Monitor Weather Bug Website.
* Monitor NWS Chat.
* Monitor Open Source Media.
* Disseminate Incident and Damage Reports resulting from Weather Events.
 | * Day-to-Day Activities.
* Maintain Situational Awareness of Weather in SE U.S.
* Track Weather Systems Approaching Georgia.
* Report Adjacent State Weather Impacts Resulting from Approaching Weather System.
* Report Impacts of Weather Systems within Georgia.
* Maintain Communications with FEMA Region IV Watch Office.
 | * Day-to-Day Activities.
* Maintain Situational Awareness of Weather in SE U.S.
* Track Weather Systems Approaching Georgia.
* Report Adjacent State Weather Impacts Resulting from Approaching Weather System.
* Report Impacts of Weather Systems within Georgia.
* Maintain Communications with FEMA Region IV Watch Office.
 |
| **ESF 1 Transportation** | * Continue Day-to-Day Activities.
 | * Develop ESF staffing Roster for SOC activation
* Determine the status of ongoing construction projects on evacuation routes
* Prepare HERO Vehicles for evacuation support in anticipation of evacuation
* Initiate planning with ESF 13 to support evacuation traffic control missions.
* Alert pre-identified staff of possible operations
* Coordinate with local EMAs to determine possible evacuation transportation assets and resource needs
* Begin procurement procedures for assets and resources
 | * Request that GDOT cease all construction projects on evacuation routes and provide status updates to Unified Command
* Coordinate with GDOT on the deployment of HERO vehicles and teams to monitor I-16 and I-95 (Atlantic Coast Threat) or I-75 (Gulf Coast Threat)
* Refine evacuation transport resource needs with local EMAs
* Determine the need for lane reversal (contraflow) along major evacuation routes.
* Monitor traffic counters to determine the impacts of increase in traffic volume from evacuee movement.
* Participate in ELT coordination calls.
 | * Continue Day-to-Day Activities.
* Develop ESF Staffing Roster for SOC activation.
* Deploy HERO vehicles and teams to assist distressed evacuees.
* In conjunction with ESF #13 deploy personnel to support evacuation traffic control missions – both along evacuation routes and at traffic control points.
* Procure and provide evacuation transportation resources to support local evacuations.
* If necessary, implement lane reversal (contraflow) on major evacuation routes.
* Monitor traffic counters to determine traffic flow increases from evacuees. Participate in ELT coordination calls.
* In conjunction with the ERB, identify, assess, and respond to evacuation- related issues.
* Coordinate needs for aerial reconnaissance for evacuation route monitoring.
 | * Continue Day-to-Day Activities.
* Develop ESF Staffing Roster for SOC activation.
* Coordinate the cessation of evacuation operations including the abatement of contraflow.
* Retract HERO vehicles and forward deployed evacuation support resources.
* Monitor traffic counters to determine traffic flow / evacuation status.
* Participate in ELT coordination calls.
* In conjunction with ESF #13 initiate planning for aerial reconnaissance for post-landfall re-entry route status.
* In conjunction with ASOC, stage aviation resources at the FSA(s) for post- landfall operations.
* In conjunction with ESF#3 initiate re-entry planning.
 |
| **ESF 2 Communications** | * Continue Day-to-Day Activities.
* Continue Planning Activities.
* Continue Equipment Maintenance.
 | * Conduct Tests of all communications equipment and alert/notification systems
* Identify communications resources to support potential Resource Requests and post-disaster operations.
* Preparatory actions to ensure all available disaster response communications equipment is prepared for deployment.
 | * Identify communications resources to support potential Resource Requests and post-disaster operations.
* Monitor communications infrastructure and provide information updates to SOC. Begin restoration efforts.
* Maintain communication with all Industry Partners and State and Federal Agency Team Members regarding the SOC activation level.
* Increase frequency of ESF 2 cross talk and input/monitoring of WebEOC.
* Prepare Communications equipment for deployment.
* Finalize the recall of any communications equipment that may have been in maintenance or on loan.
* Coordinate with ESF 7 on forward operations communications needs at the LSA, FSA (s), and other forward operations centers.
 | * Identify and possibly deploy communications resources to support requesting EMA and/or State-level operational response.
* Monitor communications infrastructure and provide information updates to SOC.
* Actively collecting communications input from responder State Agencies IOT.
* Finalize and distribute the ICS Form 205 (Incident Radio Communications Plan) to all responding agencies.
* Continue email updates to the ESF 2 Team to gain situational update.
* Finalize the recall of any communications equipment that may have been in maintenance or on loan.
* Continue coordination and planning efforts with private-sector communications providers.
* Coordinate with ESF #7 on forward operations communications needs at the LSA, FSA(s), and other forward operations centers.
 | * Identify and deploy communications resources to support requesting EMA and/or State-level operational response.
* Monitor communications infrastructure and provide information updates to SOC.
* Frequent dialog with telecom and wireless providers IOT identify all known communications issues.
* Continue email/conference call updates to ESF 2 Team IOT provide situational updates.
* Consider to activate the Wireless Emergency Alerts IOT direct the general population to the appropriate messaging available on governmental and media platforms in the affected geographic areas.
* Continue coordination and planning efforts with private-sector communications providers.
* Coordinate with ESF #7 on forward operations communications needs at the LSA, FSA(s), and other forward operations centers.
* In conjunction with ESF#3 –initiate planning for post-landfall communications needs for forward deployed response teams and forward operations centers.
* In conjunction with ESF #7 –coordinate the deployment of communications resources to the FSA(s).
 |
| **ESF 3 Public Works and Engineering** | * Continue Day-to-Day Activities.
* Continue to Monitor Water Quality.
* Continue Planning Activities.
 | * Continue Day-to-Day Activities.
* Continue to Monitor Water Quality.
* Initiate Planning Activities with re-entry task force partners for potential post-landfall debris clearing missions along access routes
 | * Continue Day-to-Day Activities.
* Continue to Monitor Water Quality
* Continue Planning Activities.
* Send out Weather Alerts and Notifications Received from the SOC.
* Coordinate with ESF 7 on potential logistical support requirements for re-entry task force.
* Continue Planning activities with re-entry task force partners for potential post-landfall access route debris clearing missions.
 | * Continue Day-to-Day Activities.
* Continue to Monitor Water Quality.
* Continue Planning Activities. Develop ESF Staffing Roster for SOC Activation.
* Send out Weather Alerts and Notifications Received from the SOC regarding potential for Severe Weather.
* Prepare templates for Public Notification Advisories.
* Identify all Drinking Water, Wastewater and Dams in the potentially impacted area.
* Continue planning activities with re-entry task force partners for potential post-landfall access route debris clearing missions.
* Place re-entry task forces on standby for deployment to support disaster operations.
* Coordinate with ESF #7 – Logistics Management and Resource Support on logistical support requirements for re-entry task forces at FSA(s).
 | * Continue Day-to-Day Activities.
* Continue to Monitor Water Quality.
* Continue Planning Activities.
* Develop ESF Staffing Roster for SOC Activation.
* Send out Weather Alerts and Notifications Received from the SOC.
* Alert our ESF 3 primary and support agencies to continue to monitor the weather and be prepared to respond to resource requests.
* Coordinate with drinking water and wastewater facilities, and advise them to inventory their resources.
* Reach out to our partner agencies such as GRWA, GAWP and GAWARN to be on stand by for possible assistance in damage assessments and/or resource requests.
* Monitor Dams for potential flood issues.
* Continue planning activities with re-entry task force partners for potential post-landfall access route debris clearing missions.
* Deploy re-entry task forces to the FSA(s).
* Coordinate with ESF #7 on logistical support requirements for re-entry task forces at the FSA(s).
 |
| **ESF 4 Firefighting** | * Continue Day-to-Day Activities.
* Continue Planning Activities.
* Continue Equipment Maintenance.
 | * Continue Day-to-Day Activities.
* Monitor for any increase in risk.
* Direct Assistance to counties when requested
 | * Continue Day-to-Day Activities.
* Send out Weather Alerts and Notifications Received from the SOC.
* Direct Assistance to counties when requested.
 | * Continue Day-to-Day Activities.
* Develop ESF Staffing Roster for SOC Activation.
* Send out to ESF 4 primary and support agencies the Weather Alerts and Notifications Received from the SOC.
* Chain Saw Strike teams put on standby for potential deployment.
 | * Develop ESF Staffing Roster for potential SOC Activation.
* Send out to ESF 4 primary and support agencies the Weather Alerts and Notifications Received from the SOC.
* Communicate with Saw crews for mobalization.
* Provide support to the SOC and other ESF partners.
 |
| **ESF 5 Emergency Management** | * Continue Day-to-Day Activities.
* SOC Activation Level - 3 (GREEN) - Active Monitoring. Actively monitor current weather conditions.
 | * Continue Day-to-Day Activities.
* SOC Activation Level - 3 (GREEN) - ACTIVE MONITORING.
* Actively monitor current weather conditions.
* Review and evaluate Damage Reports.
* Coordinate Resource and Mutual Aid Requests.
* Ensure timely production and reports of SitReps, awareness statements, and IAPs in conjunction with the planning chief.
* Participate in incident briefings with the National Hurricane Center and coordination conference calls with state partners and local EMAs.
* Coordinate with Georgia Department of Economic Development (GDEcD) to determine hotel and motel availability throughout the state to support evacuee planning.
 | * SOC Activation Level - 3 (GREEN) - ACTIVE MONITORING.
* Actively monitor current weather conditions.
* Review and evaluate Damage Reports.
* Coordinate Resource and Mutual Aid Requests.
* Request that counties provide information of special events and estimated tourist occupancy.
* Coordinate with the GDEcD to determine hotel/motel availability throughout the state; publicize the information on the GEMA website.
* Ensure timely production and reports of SitReps, awareness statements, and IAPs in conjunction with the planning chief.
* Participate in incident briefings from the National Hurricane Center and the National Weather Service and coordination conference calls with state partners and local EMAs.
 | * Develop ESF Staffing Roster for SOC Activation.
* SOC Activation Level - 2 (YELLOW) - ELEVATED ACTIVATION.
* Publish Awareness Statement to all GEMA Employees, Primary and Alternate Emergency Coordinators and all EMAs.
* Notify ESFs to increase response planning.
* Develop Staffing Roster for SOC Activation.
* Notify GEMA Staff and ESFs to report to the SOC.
* Create Incident in WebEOC.
* Convene County, State Agency, and NWS Conference Calls.
* Review and evaluate Damage Reports.
* Coordinate Resource and Mutual Aid Requests.
* Coordinate with GDEcD to determine hotel/motel availability throughout the state and publicize the information on the GEMA website.
* Ensure timely production and dissemination of situation reports, situation awareness statements, and Incident Action Plans in conjunction with Planning Section Chief.
* Participate in incident briefings from the National Hurricane Center and the National Weather Service and coordination conference calls with state partners and local EMAs.
* Initiate planning with FEMA to determine potential locations for a Joint Field Office (JFO).

  | * Develop ESF Staffing Roster for SOC Activation.
* SOC Activation Level - 3 (RED) - FULL SCALE ACTIVATION.
* Publish Awareness Statement to all GEMA Employees, Primary and Alternate Emergency Coordinators and all EMAs.
* Notify ESFs to increase response planning.
* Develop Staffing Roster for SOC Activation.
* Notify GEMA Staff and ESFs to report to the SOC.
* Create Incident in WebEOC.
* Convene County, State Agency, and NWS Conference Calls.
* Review and evaluate Damage Reports.
* Coordinate Resource and Mutual Aid Requests.
* Coordinate with GDEcD to determine hotel/motel availability throughout the state and publicize the information on the GEMA website.
* Ensure timely production and dissemination of situation reports, situation awareness statements, and Incident Action Plans in conjunction with Planning Section Chief.
* Participate in incident briefings from the National Hurricane Center and the National Weather Service and coordination conference calls with state partners and local EMAs.
* Finalize planning efforts with FEMA to determine potential locations for a Joint Field Office (JFO).
 |
| **ESF 6 Mass Care, Emergency Assistance, Housing, and Human Services** | * Continue Day-to-Day Activities.
 | * Continue Day-to-Day Activities.
* Maintain situational awareness of current and future weather conditions.
* Maintain email and phone communication with the SOC.
* Direct Assistance to counties when requested.
* Review hurricane response protocols for evacuation and sheltering operations.
* Post updated Shelter Database to GEMA website
* Coordinate with American Red Cross and Department of Human Services Division of Family and Child Services to prepare for possible sheltering
* Coordinate with ESF 11 on the identification and availability of bulk food resources to support potential sheltering and mass feeding missions
 | * Continue Day-to-Day Activities.
* Maintain situational awareness of current and future weather conditions.
* Coordinate with the American Red Cross (ARC) and Department of Human Services (DHR) Division of Family and Child Services (DFCS) to finalize preparations for possible sheltering operations. Request that shelter staff be placed on standby.
* Post an updated shelter database on the GEMA website.
* Coordinate with ESF #11 on the procurement of bulk food resources to support potential sheltering and mass feeding missions.
* Participate in ELT coordination calls for the possible influx of evacuees from threatened states
 | * Develop ESF Staffing Roster for SOC Activation.
* Maintain situational awareness of current and future weather conditions.
* Develop ESF Staffing Roster for SOC Activation.
* Establish communication with local EMAs in the potentially impacted area.
* Finalize shelter preparations and coordinate their opening where necessary. Post updated shelter database on the GEMA website.
* Coordinate with ESF #11 on the procurement of bulk food resources to support sheltering and mass feeding missions.
* Participate in ELT coordination calls to respond to the influx of evacuees from threatened states.
 | * Develop ESF Staffing Roster for SOC Activation.
* Maintain situational awareness of current and future weather conditions.
* Develop ESF Staffing Roster for SOC Activation.
* Establish communication with local EMAs in the potentially impacted area.
* Continue to coordinate and support ongoing sheltering operations. Post updated shelter database on the GEMA website.
* Continue to coordinate with ESF #11 on the procurement of bulk food resources to support sheltering and mass feeding missions.
* Participate in ELT coordination calls to respond to the influx of evacuees from threatened states.
 |
| **ESF 7 Logistics Management and Resource Support** | * Continue Day-to-Day Activities.
 | * Continue Day-to-Day Activities.
* Place LSA site and support staff on standby for potential logistics operations.
* Coordinate with Local EMAs on potential POD site locations for potential commodity distribution operations.
* Contact non-governmental logistics providers to determine readiness level and place them on alert for potential operations within 120 hours
* Coordinate with ESF 1 and ESF 13 for transportation and security resources and security escorts supporting commodity transport missions.
 | * Monitor situation for tornado/wind damage and possible support requirements.
* Coordinate with local EMAs to determine the locations of Points of Distribution (PODs) for potential commodity distribution operations.
* Finalize critical commodity requirements (Initial Response Resources, or IRR) with FEMA that may be delivered to the LSA.
* Coordinate with ESF #1 and ESF #13 on potential commodity transport missions.
* Coordinate with ESF #12 on the identification and procurement of bulk fuel resources to support forward disaster operations.
* Facilitate and document EMAC requests.
 | * Develop ESF Staffing Roster for SOC Activation.
* Monitor situation for tornado/wind damage and possible support requirements.
* Coordinate with local EMAs to determine the locations of Points of Distribution (POD) for commodity distribution operations and determine site logistical support requirements.
* Receive and stage at the LSA critical commodity shipments (IRR) from FEMA.
* Coordinate with ESF #1 and ESF #13 on potential commodity transport missions.
* Coordinate with ESF #12 on the identification and procurement of bulk fuel resources to support forward disaster operations.
* Facilitate and document EMAC requests

  | * Develop ESF Staffing Roster for SOC Activation.
* Activate the purchasing and contracting portion of ESF-7.
* Monitor situation for power outages, water system failures and homes/businesses damaged.
* Alert vendors and consider locating vendors (generators, water & tarps) in the State EOC for rapid response.
* Provide support to any State/ESF response.
* Continue to coordinate with local EMAs to determine the locations of Points of Distribution (POD) for commodity distribution operations and determine site logistical support requirements.
* Receive and stage at the LSA critical commodity shipments (IRR) from FEMA.
* Continue to coordinate with ESF #1 – Transportation and ESF #13 – Public Safety and Security Services on potential commodity transport missions.
* Continue to coordinate with ESF #12 – Energy on the identification and procurement of bulk fuel resources to support forward disaster operations.
* Facilitate and document EMAC requests.
 |
| **ESF 8 Public Health and Medical Services** | * Continue Day-to-Day Activities.
 | * Continue Day-to-Day Activities.
* Coordinate with Division of Family and Child Services to ensure personnel are prepared for possible functional needs sheltering operations.
 | * Continue Day-to-Day Activities.
* Place staff on standby for possible support of special needs shelters.
* Initiate planning to support potential medical evacuations.
* Initiate planning for potential hospital evacuations.
 | * Continue Day-to-Day Activities.
* Develop ESF Staffing Roster for SOC Activation.
* Finalize special needs shelter preparations and coordinate and support their opening where necessary.
* Coordinate and support medical evacuations. Coordinate hospital evacuations.
* Coordinate with ESF #11 on the procurement of bulk food resources to support special needs sheltering.
* Initiate planning with ESF #9 to support post-landfall medical evacuations.
 | * Continue Day-to-Day Activities.
* Develop ESF Staffing Roster for SOC Activation.
* Coordinate and support special needs shelter operations.
* Coordinate and support medical evacuations.
* Coordinate hospital evacuations.
* Coordinate with ESF #11 on the procurement of bulk food resources to support special needs sheltering.
* Continue planning with ESF #9 to support post-landfall medical evacuations.
 |
| **ESF 9 Search and Rescue** | * Continue Day-to-Day Activities.
 | * Continue Day-to-Day Activities.
* Maintain situational awareness of current and future weather conditions.
* Maintain email and phone communication with the SOC.
* Alert SRR task forces and support resources of threat level.
 | * Continue Day-to-Day Activities.
* Maintain situational awareness of current and future weather conditions.
* Maintain email and phone communication with the SOC.
* Place search, rescue, and recovery (SRR) task forces on alert for deployment to the FSA(s) to support post-landfall operations.
 | * Develop ESF Staffing Roster for SOC Activation.
* Maintain situational awareness of current and future weather conditions.
* Maintain email and phone communication with the SOC.
* Establish communication with Search and Rescue teams.
* Place SRR task forces on standby for deployment to the FSA(s) to support post-landfall operations.
* Coordinate with ESF #7 for SRR task force logistical support requirements.
* Coordinate aviation resource staging with ASOC
 | * Develop ESF Staffing Roster for SOC Activation.
* Maintain situational awareness of current and future weather conditions.
* Maintain email and phone communication with the SOC.
* Maintain communication with Search and Rescue teams.
* Initiate staging of SRR task forces for post-landfall operations.
* Coordinate with ESF #7 for SRR task force logistical support requirements.
* Coordinate aviation resource staging with ASOC
 |
| **ESF 10 Oil and Hazardous Materials Response** | * Continue Day-to-Day Activities.
 | * Continue Day-to-Day Activities.
* Maintain situational awareness of current and future weather conditions.
 | * Continue Day-to-Day Activities.
* Maintain situational awareness of current and future weather conditions.
 | * Develop ESF Staffing Roster for SOC Activation.
* Maintain situational awareness of current and future weather conditions.
* Identify potential Hazmat threats in the potentially affected areas.
 | * Develop ESF Staffing Roster for SOC Activation.
* Maintain situational awareness of current and future weather conditions.
* Identify potential Hazmat threats in the potentially affected areas.
* Initiate planning for post-landfall hazardous materials response operations.
 |
| **ESF 11 Agriculture and Natural Resources** | * Continue Day-to-Day Activities.
 | * Continue Day-to-Day Activities.
* Maintain situational awareness of current and future weather conditions.
* Initiate planning for potential animal-friendly and pet-friendly shelters, and animal congregation areas to support evacuees.
* Coordinate with ESF 6 to identify bulk food sources to support potential mass feeding missions
 | * Continue Day-to-Day Activities.
* Maintain situational awareness of current and future weather conditions.
* Initiate planning for potential animal-friendly and pet-friendly shelters, and animal congregation areas to support evacuees.
* In conjunction with ESF #6 identify and procure bulk food resources to support potential mass feeding missions.
 | * Continue Day-to-Day Activities.
* Maintain situational awareness of current and future weather conditions.
* Identify
* Coordinate with ESF 6 possible sheltering support.
* Be prepared to coordinates damages assessments if needed.
* Be prepared to provide technical assistance to public Natural, Cultural and Historic properties during damages assessment and request for assistance if needed.
* Initiate and support animal-friendly and pet-friendly shelters, and animal congregation areas.
* In conjunction with ESF #6 procure and coordinate distribution of bulk food resources to support sheltering and mass feeding missions.
* Initiate planning for the administration of the Disaster Food Stamp Program.
* Initiate planning with ESF #9 on potential animal rescue operations during post-landfall SRR missions.
 | * Continue Day-to-Day Activities.
* Maintain situational awareness of current and future weather conditions.
* Coordinate with ESF 6 possible sheltering support.
* Be prepared to coordinates damages assessments if needed.
* Be prepared to provide technical assistance to public Natural, Cultural and Historic properties during damages assessment and request for assistance if needed.
* Continue to support animal-friendly and pet-friendly shelters, and animal congregation areas.
* In conjunction with ESF #6 procure and coordinate distribution of bulk food resources to support sheltering and mass feeding missions.
* Finalize preparations for the administration of the Disaster Food Stamp Program.
* Finalize planning with ESF #9 on potential animal rescue operations during post-landfall SRR missions.
 |
| **ESF 12 Energy** | * Continue Day-to-Day Activities.
 | * Continue Day-to-Day Activities.
* Maintain situational awareness of current and future weather conditions.
* Coordinate with ESF 3 on the identification of electrical utility resources to support potential road clearing missions during re-entry.
* Coordinate with ESF 7 to identify bulk fuel resources to support mass evacuations and post-landfall disaster response operations.
 | * Continue Day-to-Day Activities.
* Maintain situational awareness of current and future weather conditions.
* Maintain communication with primary agencies and support agencies and companies.
* Coordinate with ESF #3 on the identification of electrical utility resources to support potential road clearing missions during re-entry.
* In conjunction with ESF #7 identify and procure bulk fuel resources to support forward disaster operations.
* Identify bulk fuel transportation and delivery resources to support forward disaster operations.
* Initiate coordination efforts with the Georgia Retailers Association, Georgia Association of Convenience Stores, Georgia Petroleum Council, and other relevant organizations on potential fuel shortages on evacuation routes from anticipated evacuations.
 | * Continue Day-to-Day Activities.
* Develop ESF Staffing Roster for SOC Activation.
* Maintain situational awareness of current and future weather conditions.
* Maintain communication with primary agencies and support agencies and companies.
* Coordinates with critical infrastructure owners and operators to determine the number of citizens without electrical service.
* Coordinate with ESF #3 on the identification of electrical utility resources to support potential road clearing missions during re-entry.
* In conjunction with ESF #7 identify and procure bulk fuel resources to support disaster operations.
* Initiate state fuel storage tank filling to and topping off to support disaster operations.
* Procure and stage bulk fuel transportation and delivery resources to support disaster operations.
* Initiate coordination efforts with the Georgia Retailers Association and other relevant organizations on potential fuel shortages on evacuation routes from anticipated and ongoing evacuations.
 | * Continue Day-to-Day Activities.
* Develop ESF Staffing Roster for SOC Activation.
* Maintain situational awareness of current and future weather conditions.
* Maintain communication with primary agencies and support agencies and companies.
* Coordinates with critical infrastructure owners and operators to determine the number of citizens without electrical service.
* Continue to coordinate with ESF #3 on the identification of electrical utility resources to support post-landfall road clearing missions during re-entry operations.
* In conjunction with ESF #7 identify and procure bulk fuel resources to support disaster operations.
* Finalize state fuel storage tank filling to and topping off to support disaster operations.
* Finalize the procurement and staging bulk fuel transportation and delivery resources to support disaster operations.
 |
| **ESF 13 Public Safety and Security** | * Continue Day-to-Day Activities.
 | * Continue Day-to-Day Activities.
* Monitor weather conditions and report any severe weather or damage.
* Initiate planning for security support for logistical transport missions, evacuation route monitoring (both ground and aviation based) missions.
* Coordinate with local EMAs on potential needs for law enforcement support at traffic control points during evacuations.
* Initiate planning to support check-point staffing missions during post-landfall operations that may require controlled access
* Initiate planning on possible post-landfall security operations within impacted areas.
 | * Continue Day-to-Day Activities.
* Monitor weather conditions and report any severe weather or damage.
* Assist the public on the roadways and waterways.
* Assist local Public Safety Agencies as requested.
* Request that law enforcement personnel be placed on standby for evacuation traffic operations, traffic control points, re-entry support, commodity transport security, limited access area check points, and curfew enforcement in impacted areas.
* Request that aviation resources are placed on standby for reconnaissance and damage assessment missions.
 | * Continue Day-to-Day Activities.
* Develop ESF 13 Staffing Roster for SOC Activation.
* Maintain communications between ESF 13 partner agencies.
* Monitor weather conditions and report any severe weather or damage.
* Assist the public on the roadways and waterways. Assist local Public Safety Agencies as requested.
* All ESF 13 support agencies will ensure all personnel; facilities and equipment are properly prepared for the weather risk.
* Deploy law enforcement personnel to support evacuation traffic operations, traffic control points, and lane reversal (contraflow) operations if enacted.
* Place law enforcement personnel on standby for post-landfall re-entry support, commodity transport security, limited access areas check points, and curfew enforcement in impacted areas.
* Deploy aviation resources for reconnaissance and evacuation route monitoring.
 | * Continue Day-to-Day Activities.
* Develop ESF 13 Staffing Roster for SOC Activation.
* Maintain communications between ESF 13 partner agencies.
* Monitor weather conditions and report any severe weather or damage.
* Assist the public on the roadways and waterways.
* Assist local Public Safety Agencies as requested.
* ESF 13 primary and support agencies will ensure all personnel; facilities and equipment are properly prepared for the weather risk.
* Notify critical personnel to prepare for extended shifts and emergency responses.
* Retract law enforcement personnel supporting evacuation traffic operations, traffic control points, and lane reversal (contraflow) operations.
* Place law enforcement personnel on standby for post-landfall re-entry support, commodity transport security, and limited access areas check points, and curfew enforcement in impacted areas.
* Finalize post-landfall aviation resource preparations and stage aviation resources for reconnaissance and damage assessment missions. Coordinate aviation asset staging with ASOC
 |
| **ESF 14 Long-Term Community Recovery** | * Continue Day-to-Day Activities.
 | * Continue Day-to-Day Activities.
 | * Continue Day-to-Day Activities.
 | * Develop ESF Staffing Roster for SOC Activation.
 | * Develop ESF Staffing Roster for SOC Activation.
* In conjunction with FEMA, initiate post-landfall recovery planning.
* Place Individual Assistance (IA) and Public Assistance (PA) program staff on standby for post-landfall operations within the JFO.
* In conjunction with FEMA, initiate planning for post-landfall joint preliminary damage assessments
 |
| **ESF 15 External Affairs** | * Continue Day-to-Day Activities.
* Continue planning activities.
* Continue equipment maintenance.

**Social Media:** Maintain situational awareness of weather by monitoring twitter feeds/Facebook pages of NWS offices, local meteorologists, #gawx.**Website**Continue monitoring day-to-day activities. No changes to the website. Homepage reflects the most notable weather conditions for that time of the year.  | * Continue Day-to-Day Activities.
* Prepare and distribute oress releases concerning ongoing preparedness and response actions.
* Request state and local media disseminate information about family preparedness for tropical cyclones.
* Notify external affairs personnel for potential need for assistance.
* Pending threat and scope of preparedness actions, initiate a JIC to coordinate disaster information
* Conduct media briefings from the SOC as needed.

**Social media**: Maintain situational awareness of weather by monitoring Twitter feeds/Facebook pages of NWS offices, local meteorologists, #gawx:**Website:** Continue monitoring day-to-day activities. No changes to the website. Homepage reflects the most notable weather conditions for that time of year. | * Continue Day-to-Day Activities.
* Prepare and distribute press releases concerning ongoing preparedness and response actions.
* Request state and local media disseminate information about family preparedness for tropical cyclones.
* Notify additional external affairs personnel of potential need for assistance.
* Continue to coordinate media information, press releases, and pertinent disaster information with the JIC.
* Respond to media requests and provide information / updates as needed. Conduct media briefings from the SOC as needed.

**Social media:** Maintain situational awareness of weather by monitoring Twitter feeds/Facebook pages of NWS offices, local meteorologists, #gawx:**Website:** Continue monitoring day-to-day activities. No changes to the website. Homepage reflects the most notable weather conditions for that time of year. | * Develop ESF Staffing Roster for SOC Activation.
* Coordinate with GEMA/HS meteorologist, Operations and Leadership on messaging.
* Prepare and distribute press releases concerning ongoing preparedness and response actions.
* Coordinate with Georgia Public Broadcasting (GPB) and media partners on evacuation and sheltering information dissemination.
* Continue to coordinate media information, press releases, and pertinent disaster information with the JIC.
* Respond to media requests and provide information / updates as needed.
* Conduct media briefings from the SOC upon request.

**Social media:** Maintain situational awareness of weather by monitoring Twitter feeds/Facebook pages of NWS offices, local meteorologists, #gawx:**Website:** Continue monitoring day-to-day activities. Through coordination with GEMA/HS meteorologist and Operations, the Homepage **may** reflect the enhanced risk with addition of appropriate map and links to NWS products.  | * Develop ESF Staffing Roster for SOC Activation.
* Coordinate with GEMA/HS meteorologist, Operations and Leadership on messaging.
* Prepare and distribute press releases concerning ongoing preparedness and response actions.
* Coordinate with Georgia Public Broadcasting (GPB) and media partners on evacuation and sheltering information dissemination.
* Continue to coordinate media information, press releases, and pertinent disaster information with the JIC.
* Respond to media requests and provide information / updates as needed. Conduct media briefings from the SOC upon request.

**Social media:** Maintain situational awareness of weather by monitoring Twitter feeds/Facebook pages of NWS offices, local meteorologists, #gawx, and agency partners**Website:** Continue monitoring day-to-day activities. Through coordination with GEMA/HS meteorologist Operations and Leadership, the homepage **may** reflect the moderate risk with addition of appropriate map and links to NWS products. **News Conference:** Coordinate with the Governor’s Office, Georgia Department of Administrative Services and GEMA/HS Finance to ensure that a certified American Sign Language Interpreter will be on hand if the Governor holds a news conference. |
| **GA DoD** | * Continue Day-to-Day Activities.
 | * Man JOC to level 1
* Man SOC Ga DOD desk
* Convene TAG Executive Board
* OPORD to units in GEMA RFAs
* WarnO for other units to BPT support
* Coord w/ GEMA for potential EMAC request.
 | * Validate critical personnel contact rosters.
* BPT support SOC & JOC Ops
* Identify potential resources to support potential incidents
 | * Man JOC to level 2
* Man SOC Ga DOD desk
* Convene TAG Executive Board
* WarnO distro'd to units in task org to BPT support
* Coord w/ GEMA & Governor for State Active Duty rqmnts based on situation
 | * Man JOC to level 1
* Man SOC Ga DOD desk
* Convene TAG Executive Board
* OPORD to units in GEMA RFAs
* WarnO for other units to BPT support
* Coord w/ GEMA for potential EMAC rqsts
 |
| **ISSUES & CONSIDERATIONS** | * Are Special Events scheduled for the geographic area(s) potentially impacted?
 | * Are Special Events scheduled for the geographic area(s) potentially impacted?
 | * Are Special Events scheduled for the geographic area(s) potentially impacted?
 | * Are Special Events scheduled for the geographic area(s) potentially impacted?
* Is Severe Weather anticipated to affect major metropolitan areas during normal business hours?
* Is Severe Weather anticipated to affect Transportation Hubs?
 | * Are Special Events scheduled for the geographic area(s) potentially impacted?
* Is Severe Weather anticipated to affect major metropolitan areas during normal business hours?
* Is Severe Weather anticipated to affect Transportation Hubs?
 |